## Sheet1
LOCATION | DAMAGES | REPAIRS | REPLACE EQUIPT./FURNITURE/ BLDG. REPAIRS | EXPENSES | PHOTOS
Justice Center | 2 in fire hose connection rupture on 3rd floor parking lot | Repaired Tuesday by Johnson controls |  | 549
Hwy 59 Fire Station | Sewer pipes clogged and no water pressure ( plumber checked and lines were frozen) | Pending repairs
Justice Center | 1 inch water line running from 1st floor mechanical room to 3rd floor parking lot ruptured in multiple areas including 2nd floor. Water source was shut off pending repairs. | Pending repairs
Bily Hall | 1 inch water line running from 1st floor mechanical room to 3rd floor parking lot ruptured in multiple areas including 2nd floor. Water source was shut off | Pending repairs
Fred and Anita Community Center (Peñitas) | 1 inch line Break in ceiling caused major flooding in entire building, ceilings collapsed in several areas of building. | Service Master was called in to remove water from building and begin the drying process. Line that caused the flood was repaired by our plumber but multiple leaks were discovered after. County plumber is presently working on eliminating new discovered leaks cause by freeze. | 39453.08 | 25866.06 | https://photos.app.goo.gl/NcoJbGhzkAxKbjw76
Sheriff Substation (penitas) | 1 ½ main water line break. Water source was plugged pending repairs | Pending Repairs
Records Management | 3 inch Back flow iron valves cracked causing major leak. Water was shut off. | Pending repairs from Johnson controls
Road & Bridge Dept. | Multiple water line ruptures ( 2 inch back flow valves were leaking, west mechanic shops had major line breakage, sheriff fleet water line break, Motor Pool Ice maker filters cracked, etc.) our department has temporarily repaired 9 leaks so far but more are pending |  |  | 3602.87
JP 4 Pepe Salinas | ½ inch water line break outside ( repaired | Repaired
Hwy 59 Fire Station Mobiles | 3 major water line breaks ( water was shut off pending repairs | Pending repairs
LIFE DOWNS Webb County Fair Grounds– | Multiple line breaks within grounds including stables and stage areas;water was shut off. | Pending repairs
Larga Vista Comm. Ctr. | ½ inch water line break outside of the building line was capped pending repairs and water was shut off for further inspection | Pending repairs
Rio Bravo Comm. Ctr. | Water line in kitchen area damaged walls and kitchen appliances. ( water was shut off, lines repaired custodians removed all the water from floors, building maintenance provided generators to provide power for equipment, partially removed damaged walls | Pending repairs |  |  | https://photos.google.com/album/AF1QipOFzDBU7aM0V8wt3JRB0A_ax6A_p6izQYhA2Dbv
La Presa Comm. Ctr | Line connections from water tank to the building ruptured and iron water pump cracked ( water was shut off pending complete replacement) | Pending repairs
Santa Teresita Comm.Ctr | Line connections from water tank to the building ruptured and iron water pump cracked ( temporarily connected direct line from tank to building using only gravity for minimal water pressure, pump ordered pending complete replacement ) | Pending repairs |  | 600.28
Los Botines Fire Station | Line connections from water tank to the building ruptured and iron water pump cracked. | Temporarily connected direct line from tank to building using only gravity for minimal water pressure, pump ordered and pending complete replacement. |  | 1168 | https://photos.app.goo.gl/hh5dfWfhGbiZVyqLA
Casa Blanca Gof Course | 2 inch line break outside building and an additional leak in the attic above the men's shower. Due to water damage, the ceiling collapsed. (In addition: food spoilage due to loss of electricity.) | 2 in. line break was repaired right away, water was shut off and is pending ceiling repairs.
Fernando Salinas Community Center | 1 inch back flow iron valves cracked. | Water was shut off and is pending repairs.
Quad City Fire Station | 1 inch water line rupture. | Temporarily repaired.
Casa Ortiz | 1/4 inch line ruptured at lower level of garden. | Water was shut off and is pending repairs.
Mirando Community Center | Multiple 3/4 copper lines ruptured in the library retroom area causing flooding inside and ceiling collapsed. | Outside panels were removed to access water lines and were temporarily repaired, flood water was removed. Water was shut off for further inspection. Pending ceiling repairs.
Self Help Center on Hwy 359 | Multiple 3/4 copper lines ruptured outside building. | 4 Line ruptures repaired.
Commissioner's Courthouse | Irrigation backflow leaking. | Water was shut off and is pending repairs.
Agriculture Bldg. USDA | line ruptures; damaged concrete water troughs | pending repairs |  | 1460
Water Utilities | Wastewater Treatment Plant-Vacuum Truck Hydraluic Pump Assembly Cracked Water Treatment Plant and Distribution System- River pump motor, transfer pump motorm polymer pump motor, UV chamber system, high service pump air release valve & 5 lamps, curve stops, billing office card reader system Colorado Acres Dispenser- gauges, unloading pump motor, 2" backflow preventers, piping and fittings | Curve stop-replaced Gauges-ordered 2"backflow preventers-in process Piping and fitting-ordered |  | 134630.69
|  | TOTALS: | 39453.08 | 167876.9