## Sheet1
VE Summary
Project: Webb County Sheriffs Office Renovation
Items | Description |  | VE Budget | Comments | A/E Response
1 | Electrical
| VE Aluminum Feeders, Switch Gear |  | 235000
| VE Light Fixtures |  | 175000
|  | Total: | 410000
2 | HVAC
| SCR Heat to Staged Heat |  | 10000
| Comparative Enthalpy Ecomomizer to Dry Bulb Economizer |  | 1200
| Convenience Outlets - Delete |  | 1750
| Hinged Access Panels to Bolted Access Panels |  | 650
| Wind Rated Curbs to non Wind Rated Curbs |  | 5000
| Compressor Soung Blanket- Delete |  | 375
| Change RTU-A4 to next level down- two unit |  | 8000
|  | Total: | 26975
3 | Plumbing
| VE Fixtures |  | 40550
|  | Total: | 40550
4 | Flooring & Wall Tile
| Membrane |  | 60000
| Tile 8200 sqft-Wall-to reduce 1/2 sqft |  | 32800 |  | Will review
| Tile to VCT |  | 87856 | $2.00 VCT allowance | Please review this credit. Tile specified is roughly $2.60/sf material cost.
|  | Total: | 180656
5 | ACT
| Clouds |  | 19728
|  | Total: | 19728
6 | Interior Door STC rating
|  | 108460 | 26600 | Remove STC Rating
| Hardware Allowance | 90000 |  | Owner Allowance
|  | Total: | 26600
7 | Concrete Floor Demo
| Saw Cut Demo & Dispose |  | 19800
| Concrete |  | 28350
|  | Total: | 48150
8 | Second Floor Finish-out
|  |  | 24000 | Plumbing-
|  |  | 27589 | Electrical-
|  |  | 11613 | Mechanical-
|  |  | 9000 | Paint-
|  |  | 14800 | Framing/ACT/Drywall- Labor
|  |  | 9228.93 | Framing/ACT/Drywall- Material
|  |  | 23688 | Flooring
|  |  | 2085 | Doors
|  |  | 6700 | Storefronts
|  |  | 1500 | Accessories
|  |  | 2500 | Partitions
|  |  | 3480 | Exterior Stucco
|  | Total: | 136183.93
9 | Alternate 5
| Deduct Racks |  | 68098 |  | We need to include all FFE in this project. We can back it out of your cost and use it as an allowance to avoid GC fees.
10 | Drop Ceilings to 10 feet
| Reduce Mtl Stud Height / Drywall/ Remove Act |  | 54082 |  | We can drop the ceilings to 10 feet to save costs. Includes Removeing ceiling on drawing
11 | Remove all exterior metal panels; repaint exterior only
|  |  | 38600 | Wall Panels
|  |  | 13800 | Canopys
|  |  | -9580 | paint- add
|  | Total: | 42820
12 | Replace Decorative Concrete Block with 8 x 8 decorative CMU
|  |  | 1700 | Labor
|  |  | 3867 | material
|  | Total: | 5567
13 | Remove Temporary Sidewalk Shelters; Utilize temporary fencing |  | 24586 | matl & labor
|  | VE Total: | 1083995.93
OTHER COSTS
| IT Cabling |  |  | Included in Base Bid
| CURRENT BASE BID |  | 6697507
| VE BID |  | 5613511.07
OWNER PROVIDED ITEMS (NOT IN CONSTRUCTION BUDGET)
| Network/IT and Phone Equipment |  | 115980.04
| Furniture and Equipment |  |  | Not Included. By owner
| Owner Racks |  | 68098
| Full Generator Option |  | 287725
| TOTAL PROJECT COST |  | 6085314.11

## FINAL VE SUMMARY
VE Summary
Project: Webb County Sheriffs Office Renovation
Items | Description |  | VE Budget | Comments | A/E Response
1 | Electrical
| VE Aluminum Feeders, Switch Gear |  | 235000
| VE Light Fixtures |  | 175000
|  | Total: | 410000
2 | HVAC
| SCR Heat to Staged Heat |  | 10000
| Comparative Enthalpy Ecomomizer to Dry Bulb Economizer |  | 1200
| Convenience Outlets - Delete |  | 1750
| Hinged Access Panels to Bolted Access Panels |  | 650
| Wind Rated Curbs to non Wind Rated Curbs |  | 5000
| Compressor Soung Blanket- Delete |  | 375
| Change RTU-A4 to next level down- two unit |  | 8000
|  | Total: | 26975
3 | Plumbing
| VE Fixtures |  | 40550
|  | Total: | 40550
4 | Flooring & Wall Tile
| Membrane |  | 60000
| Tile 8200 sqft-Wall-to reduce 1/2 sqft |  | 32800 |  | Will review
| Tile to VCT |  | 0 |  | NOT ACCEPTED ($87,856 SAVINGS)
|  | Total: | 92800
5 | ACT
| Clouds |  | 19728
|  | Total: | 19728
6 | Interior Door STC rating
| Remove STC (Soundproofing at Doors) | 108460 | 0 |  | NOT ACCEPTED ($26,600 SAVINGS)
| Hardware Allowance | 90000 |  | Owner Allowance
|  | Total: | 0
7 | Concrete Floor Demo
| Saw Cut Demo & Dispose |  | 19800
| Concrete |  | 28350
|  | Total: | 48150
8 | Second Floor Finish-out
|  |  | 24000 | Plumbing-
|  |  | 27589 | Electrical-
|  |  | 11613 | Mechanical-
|  |  | 9000 | Paint-
|  |  | 14800 | Framing/ACT/Drywall- Labor
|  |  | 9228.93 | Framing/ACT/Drywall- Material
|  |  | 23688 | Flooring
|  |  | 2085 | Doors
|  |  | 6700 | Storefronts
|  |  | 1500 | Accessories
|  |  | 2500 | Partitions
|  |  | 3480 | Exterior Stucco
|  | Total: | 136183.93
9 | Alternate 5
| Deduct Racks |  | 68098 |  | We need to include all FFE in this project. We can back it out of your cost and use it as an allowance to avoid GC fees.
10 | Drop Ceilings to 10 feet
| Reduce Mtl Stud Height / Drywall/ Remove Act |  | 54082 |  | We can drop the ceilings to 10 feet to save costs. Includes Removeing ceiling on drawing
11 | Remove all exterior metal panels; repaint exterior only
|  |  | 38600 | Wall Panels
|  |  | 13800 | Canopys
|  |  | -9580 | paint- add
|  | Total: | 42820
12 | Replace Decorative Concrete Block with 8 x 8 decorative CMU
|  |  | 1700 | Labor
|  |  | 3867 | material
|  | Total: | 5567
13 | Remove Temporary Sidewalk Shelters; Utilize temporary fencing |  | 24586 | matl & labor
|  | VE Total: | 969539.93
OTHER COSTS
| IT Cabling |  | - | Included in Base Bid
| CURRENT BASE BID |  | 6697507
| VE BID |  | 5727967.07
OWNER PROVIDED ITEMS (NOT IN CONSTRUCTION BUDGET)
| Network/IT and Phone Equipment |  | 115980.04
| Furniture |  | 260000
| Owner Racks |  | 68098
| Full Generator Option |  | 287725
| TOTAL PROJECT COST |  | 6459770.11